## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
|  |  | Incorrect amenities recommended for guests (e.g., business traveler recommended a kids' play area) | Sprint 4 | Intern | Incorrect Recommendation | Updated model tuning parameters | 2025-01-25 | Closed | Fixed with better customer profiling
|  |  | Negative review was not detected and no alert was triggered for staff | Sprint 4 | Intern | Missed Sentiment | Adjusted sentiment detection thresholds | 2025-01-25 | Closed | Retrained model with more diverse data
|  |  | Staff was not notified about a critical customer complaint in the review data | Sprint 4 | Intern | Notification Failure | Fixed API call for staff alerting | 2025-01-25 | Closed | Tested with multiple scenarios
|  |  | Some customer preferences were missing in the final dataset used for AI recommendations | Sprint 4 | Intern | Missing Data | Improved data collection pipeline | 2025-01-25 | Closed | Added validation checks

## Sheet2
Logical
User Interface
Maintainability
Standards
Others